## Sheet1
Project Tasks
Task | Description | Output for documentation | Owner
Import Data, Basic Merging | Load raw files, assign column names. Create data matrix | NA | Luis
Handle Missing values | For example not all artists have genres | % of missing values, list of steps taken to handle it
Process text columns | Categorical columns, columns with concatenated text | Summary of processing applied
Normalize Weights | "Weights" or plays by user differ, my top artist my have 1,000 plays but your top artist might have 500 plays. Reasearch, test and select a way to normalize this weights for good performance when fitting models | Visual of different weights among users, visual of impact on computing distances among users, criteria for method selected
Balance Popular vs Non-mainstream artists | Some artists will be very popular amog users. Most artists will be only heard by a handful of users. Models will might learning from the not so popular artists. Visualize this scenario, research, test and pick a method to "normalize" or handle this situation. | Plot of the distribution of artist plays, criteria for method seelction
Sampling Strategy | Do we have too much data? Yes or no? if Yes, research test and select a method for downsampling if no skip this task | Run times (efficiency gains) before and after downsampling.
Research Evaluation Methods for clustering | With clustering we don't have a "label" to validate agains. Research what we can do instead and pick a method for our project | brief comparison of methods, criteria for selected method. Python functions or library required to compute metrics
Pick a method to visualize clusters | Give our data is high dimensional what alternatives we have to visualize clusters? | Visualize the clusters (dim reduction can be applied just for visualization). Or word clouds since we have Tag Data. Python functions or library required to compute metrics
Prototype Clustering Models | Fit K-Means vs Spectral Clustering (or another method) Assess the results qualitatively , for example explore a cluster | Visualization, metrics, criteria for selection of the final method | Luis
Research creation of synthetic samples | We are creating a clustering model. The outout will be plugged into another model that ranks recommendations based on novelty (real discovery not just the most popular artist) . Research test and pick a method for this. We discussed synthetic artists but it could be another method. Purpose is to allow for the scenario where not all artists will be on the lastfm user-artis dataset, but still, the recommendation might include such artist because it is similar according to the spotify data | brief comparison of methods, criteria for selected method. Python functions or library required to compute metrics
Pick a method to visualize ranked recommendations | Not sure about this, just adding it because many human beings are visual so it might help. But not a priority perhaps | not sure…
Prototype Ranking Model | Given a subset of relevant artists for recommendation, rank them in order of novelty. We want the user to be pleasently surprised. Fit Naïve Bayes or other classifiers for example logistic regression (requires a method for train test split), or treat novelty as anomaly detection | metrics, criteria for selection of the final method, quantitative metrics of performance
Mid Project Check in (30min Whatsapp or Zoom) | We should set a date, maybe July 30th? | Agree on dropping a task, adding a task. And final alogirithym choice for the 2 models | All
Fit Models with final parameters and plug them together into 1 process | Technical - Plug Everything together into a single noteboook | Visualizations, metrics, tables, runtime
Qualitative Tests | Given the list of artist listened by an unseen user, provide a ranked recommendation of the artists they might enjoy exploring. Add a qualitatively | Visualizations, metrics, tables | Each can take 2 user IDs and make sense of the reccomendation
Create Document Structure | The skeleton of the sections that our document will include. Focus on storytelling and trying to include as much statistical stuff that shows rigurosity applied to our methods | Document with sections and sub-sections
Collect output for documentation and fit it into the document structure | Plug our notes into the structure | Text for report
Project Learnings, Conclusions and Next Steps | The "So, what?" of our project. What did we learn and why is it important | Text for report
Report Quality Check (1hr - ZOOM Call) | We should set a date, maybe August 1st at night? | List of adjustments to apply to the report | All
Quick Tuning for Models/Code | Adjustments in model validation, assumptions, sampling method, or adding tests | Output from adjustments | Adjustments will be split during Zoom Meeting
Document Adjustments | Add adjustments to report | Text for report